## Sheet1
Risk Matrices
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | High
Very Likely | Low medium | Medium | Medium high | High | High
Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level
BP | Back pain might start being noticieable. | Ensure I practice some movement every day. | Keep good health throughout the development. | Moderate | Major | Medium
ICF | Internet connectivity could fail. | Have a backup internet connection from a mobile device. | Maintain online connection with repositories and Jira servers. | Unlikely | Major | Low medium
CF | Computer hardware or Operational System might fail. | Ensure there is a backup computer nearby available. | Have availabe machines for work at all times and prevent delays. | Very Unlikely | Catastrophic | Medium
INT | Frequent interruptions to anwer requests not related to the project. | Allocate a specific timeslot during the day to respond requests. | Reduce impact by limiting time required for other activities not related to the project. | Likely | Hazardous | Medium high
MEET | Excessive meetings with little outcome. | Agree with management meetings should be limited to 30mins and only on mornings. | Reduce time allocated for non productive work. | Moderate | Major | Medium
CIR | Change in the requirements for items that have been already coded. | Negotiate a Minimum Viable Product that does not include the impacted requirement. | Minimise the impact on the delivery date. | Very Unlikely | Minor | Low
UE | Understimated effort for critical devepment tasks | Negotiate with management more resources (people or time) to finish the tasks. | Minimise the impact on the delivery date. | Unlikely | Minor | Low